Sprint — Ready to Execute

Everything the team can do in full right now, independent of the client meeting. Meeting scheduling runs in parallel, not in sequence.

Sprint goal: By sprint close: staging.hms.zensynq.com is genuinely live and externally verified; the onboarding wizard and tenant screens are component-consistent and demo-ready under the current look; two carried-forward hygiene gaps are closed; every claim in the closing report has real pasted evidence, per standard.

Theme decision parked, not dropped. The visual-direction question (theme-switch-pack, A/B/C) is set aside for now per direction — no theme work in this sprint. It stays available to pick up later without any lost work; nothing here depends on it. This sprint focuses on making the CURRENT look properly finished, since 'details not good' is a real, separate issue from which palette eventually gets chosen.

# Track 1 — Screen Detail Polish (wizard + tenant screens, current theme)

| ID | Ticket (acceptance gist) | Owner | Traces / dep |
| --- | --- | --- | --- |
| T1-01 | Component consistency pass: Tenant Management + Onboarding Wizard Steps 1–4 use Card/FieldCell/StatusPill consistently instead of plain bordered inputs/divs. | Frontend | prior plan |
| T1-02 | Add proper loading/empty/error states to every onboarding-path screen per the standard Definition of Done — likely skipped when these screens were built quickly as operator tooling. | Frontend | DoD |
| T1-03 | STAFF_ENROLLED: implement the real MFA-enrollment check, or rename the label honestly if that data isn't available yet. Update the onboarding test to assert actual behavior, not just count. | Backend+FE | standing item |
| T1-04 | Ops Control screen: same component-consistency pass, lower priority than the wizard but same standard once time allows. | Frontend | secondary |
| T1-05 | Dry run: walk the full 8-step onboarding lifecycle (provision → go-live) yourself on the polished screens; confirm nothing looks unfinished anywhere in the path. | Frontend | dep T1-01..04 |

# Track 2 — Real Staging Deployment (full, no client dependency)

| ID | Ticket (acceptance gist) | Owner | Traces / dep |
| --- | --- | --- | --- |
| T2-01 | DNS: A record for staging.hms.zensynq.com; confirm propagation before proceeding. | Infra |  |
| T2-02 | Harden the VPS: firewall (22/80/443 only), SSH key-only, fail2ban, unattended upgrades. | Infra |  |
| T2-03 | Deploy current main of both repos with production env vars: real secrets, ALLOW_DEV_TOKENS=false, ENV not development. | Infra+Backend |  |
| T2-04 | TLS via certbot; enable nginx 443 + HSTS; confirm port 8000 not publicly exposed. | Infra |  |
| T2-05 | External verification: curl -I https://staging.hms.zensynq.com/health from a machine that is NOT the VPS. Paste literal output. | Infra | evidence required |
| T2-06 | Confirm dev tokens rejected on staging: curl with a dev Bearer token against a protected endpoint, expect 401. | Backend | evidence required |
| T2-07 | Run both flagship Playwright specs against staging (E2E_BASE_URL=https://staging...), twice consecutively. | Frontend | evidence required |
| T2-08 | Off-box encrypted backup + one test restore ON staging specifically; confirm passphrase handling. | Infra | evidence required |

# Track 3 — Platform Hygiene

| ID | Ticket (acceptance gist) | Owner | Traces / dep |
| --- | --- | --- | --- |
| T3-01 | Tenant offboarding/cascade-delete: replace the ad hoc manual DELETE chase with a real script or ON DELETE CASCADE on tenant-scoped FKs — one safe operation to remove a tenant. | Backend | found during demo prep |
| T3-02 | TEN-301–304 (subscription invoicing, Aarogyasri aggregates, suspend, override): produce real pytest + curl evidence for each. Reconfirm suspend/override still carry the cross-tenant isolation test. | Backend | standing gap |
| T3-03 | Re-confirm CI required-checks (gh api ... --jq '.required_status_checks.contexts') on both repos after this sprint's merges. | Both | N1 criterion 5 re-check |

# Parallel, Non-Engineering: Schedule the Client Meeting

Send the decision list and proposed agenda (already prepared) to the client this week, independent of sprint progress — minus the theme item, which is on hold. The remaining decisions (flag F1, migration ownership, go-live approval, plan naming, staging/ABDM timelines) don't need theme work finished to discuss.

# Sequencing

All three tracks run in parallel with no cross-dependencies. Track 2 (staging) is the largest and should not slip — if VPS/DNS access sits outside this sprint's active contributors, loop them in today. Track 1 and Track 3 can proceed on the existing dev stack without waiting on Track 2.

# Exit Criteria

| Track | Done means |
| --- | --- |
| 1 | Wizard and tenant screens are component-consistent (Card/FieldCell/StatusPill throughout); all 4 states (loading/empty/error/success) present; STAFF_ENROLLED accurate; full lifecycle dry-run complete under the current theme. |
| 2 | staging.hms.zensynq.com reachable via curl -I from outside the VPS with valid TLS; dev tokens rejected; both flagship specs green against staging twice; one tested backup restore on staging. |
| 3 | Tenant deletion is a single safe operation; TEN-301–304 each have real pasted evidence; CI required checks reconfirmed. |

When the client meeting happens — this week or next — it walks a genuinely finished demo and a live staging environment, and works through the decision list minus the theme question. Visual direction stays available to revisit any time, with zero rework lost, since it was set aside rather than half-built.