HMS — Next Sprints Plan (N1–N5)

Combined backend (hms-platform) + frontend (hms-web) · from feature-complete-on-mocks to onboarded tenants on staging

Supersedes sequencing in prior plans; ticket IDs from TEN plan carried over · July 2026

# Contents

# 0. Where We Are & Plan Logic

Both repos are feature-complete but unproven: the UI has run only against MSW mocks, the backend's nine bulk-built modules have never served the real UI, auth is a dev stub on both sides, and neither repo is under version control. The client's next commercial ask is end-to-end tenant management/onboarding, with a governed Platform Control Center behind it. The plan therefore runs: protect & integrate (N1) → real auth & staging (N2) → tenant onboarding (N3–N4 = TEN T1/T2) → control center + hardening (N5), with ABDM as a parallel workstream from N2 because its 3–6 month clock must start now. Cadence stays 2-week sprints; both teams work the same sprint on coupled tickets.

Sprint N1 cannot start on unversioned code. Day 1, hour 1 of N1 is git init/commit/push + branch protection on BOTH repos (ticket N1-00). Integration means bisecting, reverting, and diffing — impossible without history. No other ticket may merge before N1-00 is done.

# Sprint N1 — Protect & Integrate (the truth sprint)

Goal & demo: MSW off; the full UI runs against the real FastAPI stack; both flagship Playwright specs green against docker compose; backend test suite verified. Demo: live end-to-end walkthrough of both flagship flows on the compose stack, plus CI running on both repos.

| ID | Ticket (acceptance gist) | Team | Traces / dep |
| --- | --- | --- | --- |
| N1-00 | Version control both repos: init on main, baseline commit, push, branch protection (PR + CI required); .gitignore verified (env, egg-info, node_modules, dist). | Both | BLOCKER · 0.5d |
| N1-01 | Backend suite verification: run full pytest; fix reds; confirm the isolation test covers EVERY tenant-scoped table added by the nine modules (add missing cases); wire suite into CI on push. | BE | PLT-002 gate |
| N1-02 | Seed expansion: realistic synthetic dataset (2 tenants × ~50 patients, schedules, encounters, orders, invoices, referrers, prereq library) so real-data screens aren't empty-state-only. | BE | supports N1-03+ |
| N1-03 | MSW-off integration, wave 1: patients + scheduling + check-in against live API; fix contract breaks on whichever side violates the FRD; regenerate + commit schema per backend fix. | FE+BE | REG/SCH/REF-061 |
| N1-04 | Integration wave 2: EMR + Rx + next-visit follow-up; verify 409-duplicate shape, alert/override payloads, DRAFT follow-up creation against real API. | FE+BE | EMR-013/RX-003 · dep N1-03 |
| N1-05 | Integration wave 3: orders/results + billing/till + referral timeline + portal reads; verify result flags, invoice splits, Aarogyasri indicator fixtures. | FE+BE | ORD/BIL/REF-064 · dep N1-04 |
| N1-06 | Playwright specs against live compose (not MSW): both flagship flows green headless in CI; MSW retained only as an explicit dev mode flag. | FE | UI-605 truly passes |
| N1-07 | Telemetry/PII scrub verification against REAL response shapes; audit-event spot check: every patient-data screen action lands an audit row. | FE+BE | PLT-005, UI-703 |
| N1-08 | Contract debt log: every mock-vs-real mismatch recorded with which side changed and why — feeds FRD errata and prevents silent spec drift. | Both | process |

# Sprint N2 — Real Auth & Staging (client-visible milestone)

Goal & demo: Keycloak/OIDC live on both sides with MFA; full stack deployed to staging.hms.zensynq.com over HTTPS with backups; client demo delivered from staging. Demo: login via real OIDC with TOTP, run both flagship flows on staging from a phone and a laptop.

| ID | Ticket (acceptance gist) | Team | Traces / dep |
| --- | --- | --- | --- |
| N2-01 | Keycloak deployment (compose service): realm, clients, tenant+role claims, TOTP MFA policy; admin bootstrap documented. | BE | TEN-106a |
| N2-02 | Backend token validation: hms_auth internals replaced with OIDC JWT verification producing the same RequestContext; dev tokens rejected outside dev flag; auth failures audited. | BE | IAM-001/006/007 · dep N2-01 |
| N2-03 | Frontend AuthProvider swap: OIDC code+PKCE flow, silent refresh, logout; screens untouched (verified by zero diffs outside auth/); session-expiry mid-form preserves input. | FE | IAM-003 · dep N2-02 |
| N2-04 | Staging deploy: VPS hardened per checklist, DNS staging.hms.zensynq.com, TLS+HSTS, nginx serving web+api same-origin, 8000 unpublished, hourly encrypted off-box backups + one tested restore. | BE | DEV_SETUP §B |
| N2-05 | Staging smoke + E2E: Playwright specs against staging; uptime/health monitoring + alert to ops channel. | FE+BE | dep N2-04 |
| N2-06 | Client demo pack: walkthrough script (both flows + portal), demo tenants reset script, recording; F1 (DRAFT follow-up) formally signed off in the demo meeting. | Both | U7 script, flag F1 |

# Sprint N3 — Tenant Onboarding I (executes TEN T1)

Goal & demo: An operator provisions a new tenant; its admin logs in via OIDC invite, completes the Setup Wizard, invites MFA-enrolled staff — under 30 minutes, recorded. Tickets TEN-101…TEN-108 as specified in the Tenant Management & Onboarding plan (provision API + lifecycle states, Operator Console shell with separate auth audience, editable config APIs + Admin Console v2, sites/services/charge-master setup, invite flow, Setup Wizard v1). TEN-106 shrinks to claim-mapping work since Keycloak landed in N2.

Ticket detail lives in HMS-Tenant-Onboarding-Plan §3; this sprint imports them unchanged. Add here: N3-X1 (Both) — operator-route boundary test joins CI (tenant token can never reach operator endpoints), per the two-console rule.

# Sprint N4 — Tenant Onboarding II (executes TEN T2)

Goal & demo: A 500-row legacy CSV is imported, reconciled through the clinician gate, readiness checklist goes green, operator flips the tenant LIVE, and a full FHIR export downloads. Tickets TEN-201…TEN-208 (Migration Workbench with staged imports, critical-data clinician confirmation, readiness checklist engine, go-live flow, attestation service, operate views, offboard/export).

Ticket detail in HMS-Tenant-Onboarding-Plan §4. Client decisions (a)–(c) from that plan's §5 — package names, who drives migration, operator-approved go-live — must be confirmed before N4 planning; chase them during N2's demo meeting. Exit of N4 = the client's 'end-to-end tenant management and onboarding' acceptance recording (plan §6).

# Sprint N5 — Platform Control Center & Hardening (executes T3)

Goal & demo: The operator sees and manages the whole platform: health wall, tenant vitals, flags, audited support impersonation with tenant-visible disclosure, break-glass with second approver, alerting. Demo: monitor → act → impersonate with banner → show the hospital's own audit recording it.

| ID | Ticket (acceptance gist) | Team | Traces / dep |
| --- | --- | --- | --- |
| TEN-301/302 | Operator metrics API (PHI-free by construction) + Control Center dashboard: health wall, tenant grid, activity stream, alert badges. | BE+FE | see T3 spec |
| TEN-303 | Manage actions with reason + audit: flags, suspend/resume, force-logout, jobs, announcements. | BE+FE | — |
| TEN-304 | Support impersonation: token exchange, banner, time-box, patient-content exclusion default, tenant-visible audit entry. | BE+FE | dep OIDC |
| TEN-305 | Break-glass inspection: coded reason + ticket ref, second approver beyond single record, per-record logging, tenant disclosure. | BE+FE | IAM-004 pattern |
| TEN-306/307 | Alerting rules → ops channel; boundary tests extended (operator cannot write clinical data outside break-glass) into permanent CI gate. | BE | — |
| TEN-308 | Tenant transparency view: operator accesses visible in the hospital's own audit screen. | FE | trust feature |
| N5-X1 | Performance/load sanity on staging at NFR-ish volumes (seeded 50k patients one tenant): patient search <2s, summary <3s measured. | BE+FE | NFR |

# Parallel Workstream P — ABDM (starts in N2, runs through N5+)

ABDM is 3–6 months of calendar time driven by external certification; it cannot wait for a sprint slot. One engineer (rotating pair) owns it continuously: P-1 sandbox registration + credentials (N2); P-2 ABHA create/verify at registration wired into REG + the registration UI's ABHA field (N3); P-3 HFR facility + HPR provider linkage in tenant onboarding (N4 — lands naturally inside the Setup Wizard as an 'ABDM' step for Indian tenants); P-4 FHIR conformance for M1 records + sandbox milestone testing (N5). Certification submission targets end of N5; production ABDM follows in the release train after.

# Exit Summary & Risks

| Sprint | Exit criteria (all required) |
| --- | --- |
| N1 | Both repos on protected main with CI; backend suite green incl. extended isolation coverage; MSW off; both Playwright flows green vs compose; contract-debt log written |
| N2 | OIDC+MFA on staging; staging HTTPS live with tested backup restore; client demo delivered from staging; F1 signed off |
| N3 | New-tenant provision→configured→staffed <30 min recorded; operator-route boundary test in CI |
| N4 | Full onboarding acceptance recording per TEN plan §6; client decisions (a)–(c) resolved |
| N5 | Control Center demo (monitor→act→impersonate→tenant-visible audit); load sanity numbers recorded; ABDM sandbox milestones on track |

Top risks: integration surfacing deep backend defects in the bulk-built modules (buffer: N1 has no feature tickets, only truth-finding; spill into early N2 is acceptable, staging slips a week); Keycloak learning curve (mitigate: N2-01 starts day 1 of N2 with the compose service, not mid-sprint); client decision latency on TEN §5 items (chase at the N2 demo, or N4 plans to the recommended defaults); ABDM external dependencies (owned continuously, never parked). Standing rule unchanged: synthetic data only until production infrastructure and counsel sign-offs exist.